## Sheet1
|  |  |  | 2023-04-05 |  |  |  |  | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01
|  |  |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Task | assigned to | start | end | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5
Backend & functionality | bar: 2023-04-24 T 25
decide on framework | Team | 2023-04-05 | 2023-04-13 | bar: 2023-04-05 W 5 to 2023-04-10 T 13; 2023-04-24 T 25
set up a DB | Zane & Zach & kareem | 2023-04-05 | 2023-04-20 | bar: 2023-04-05 W 5 to 2023-04-17 T 20; 2023-04-24 T 25
download data for testing | Zane & Zach | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
functionality to save user account information | Zane & Zach | 2023-04-13 | 2023-04-27 | bar: 2023-04-10 T 13 to 2023-04-24 T 27
functionality for login screen | Zane & Zach & Team | 2023-04-13 | 2023-04-27 | bar: 2023-04-10 T 13 to 2023-04-24 T 27
Store/download .csv/database files | Zane & Zach & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
functionality to compare test/solution data accuracy using metrics | Kareem | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
create method for contributor to upload TS data & forecasting task | Zane & Zach & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
create method for participant to download forecasting task and training dat | Zane & Zach & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
create method for participant to upload solution data to a forecasting task | Zane & Zach & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
Integration and Debugging | bar: 2023-04-17 T 20 to 2023-05-01 M 1
Integrate frontend/backend | Team | 2023-04-29 | 2023-05-05 | bar: 2023-04-24 T 25; 2023-04-24 S 29 to 2023-05-01 F 5
debug views | Team | 2023-04-29 | 2023-05-05 | bar: 2023-04-24 T 25; 2023-04-24 S 29 to 2023-05-01 F 5
debug comparison metrics | Team | 2023-04-29 | 2023-05-05 | bar: 2023-04-24 T 25; 2023-04-24 S 29 to 2023-05-01 F 5
debug file conversion | Team | 2023-04-29 | 2023-05-05 | bar: 2023-04-24 T 25; 2023-04-24 S 29 to 2023-05-01 F 5
Frontend/UI design | bar: 2023-04-24 T 25
create UI design | Erin | 2023-04-13 | 2023-04-20 | bar: 2023-04-10 T 13 to 2023-04-17 T 20; 2023-04-24 T 25
Create login page | Aiden & Erin & Team | 2023-04-13 | 2023-04-27 | bar: 2023-04-10 T 13 to 2023-04-24 T 27
create contributor page | Aiden & Erin & Team | 2023-04-13 | 2023-04-27 | bar: 2023-04-10 T 13 to 2023-04-24 T 27
create participant page | Aiden & Erin & Team | 2023-04-13 | 2023-04-27 | bar: 2023-04-10 T 13 to 2023-04-24 T 27
present statistical comparisons (and graphs?) to participant upon upload of solution data | Aiden & Erin & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
create page for contributor to upload TS data & forecasting task | Aiden & Erin & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
create page for participant to download forecasting task and training dat | Aiden & Erin & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
create page for participant to upload solution data to a forecasting task | Aiden & Erin & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
create admin page | Aiden & Erin & Team | 2023-04-20 | 2023-05-01 | bar: 2023-04-17 T 20 to 2023-05-01 M 1
Desgin | bar: 2023-04-24 T 25
SRS Document | Zane & Team | 2023-04-05 | 2023-04-24 | bar: 2023-04-05 W 5 to 2023-04-24 T 25
SDS Document | Team | 2023-04-05 | 2023-04-24 | bar: 2023-04-05 W 5 to 2023-04-24 T 25
design SW architecture | Team | 2023-04-05 | 2023-04-24 | bar: 2023-04-05 W 5 to 2023-04-24 T 25
Organization & Outputs | bar: 2023-04-24 T 25
distribute tasks | Team | 2023-04-05 | 2023-04-17 | bar: 2023-04-05 W 5 to 2023-04-17 T 18; 2023-04-24 T 25
set up git repository | Zane | 2023-04-05 | 2023-04-05 | bar: 2023-04-05 W 5; 2023-04-24 T 25
set up trello | Aiden | 2023-04-05 | 2023-04-05 | bar: 2023-04-05 W 5; 2023-04-24 T 25
set up google drive | Aiden | 2023-04-05 | 2023-04-05 | bar: 2023-04-05 W 5; 2023-04-24 T 25
set up discord | Erin | 2023-04-05 | 2023-04-05 | bar: 2023-04-05 W 5; 2023-04-24 T 25
Team Meetings | Team | recurring | bar: 2023-04-10 M 10; 2023-04-10 T 13; 2023-04-17 M 17; 2023-04-17 T 20; 2023-04-24 M 24 to 2023-04-24 T 25; 2023-04-24 T 27; 2023-05-01 M 1; 2023-05-01 T 4
Progress Meetings | Team | recurring | bar: 2023-04-17 T 18; 2023-04-24 T 25
Project presentations | Team | 2023-05-03 to 2023-05-05 | bar: 2023-04-24 T 25; 2023-05-01 W 3
project due | Team | 2023-05-05 to 2023-05-09 ????? | bar: 2023-04-24 T 25